|  | EUROPEAN COMMISSION 6th FRAMEWORK PROGRAMME |  |
| --- | --- | --- |

Network of Excellence HySafe

“Safety of Hydrogen as an Energy Carrier”

Contract No SES6-CT-2004-502630

Minutes of the HYTUNNEL Kick-off Meeting

at BRE Watford, London, UK

April 22nd, 2005

S. Miles, BRE

Draft Version 1

Participants

| Party # | Party Abbreviation | Participant |
| --- | --- | --- |
| 1 | FZK | Alexei Kotchourko |
| 4 | BMW | Claus Schitter |
| 5 | BRE | Suresh Kumar |
| 5 | BRE | Stewart Miles |
| 5 | BRE | Martin Shipp (guest) |
| 5 | BRE | Corrine Williams (guest) |
| 12 | INASMET | Estibaliz Ezponda |
| 16 | NCSRD | Alexandros Venetsanos |
| 20 | UC | Luc Bauwens |
| 21 | UNIPI | Marco Carcassi |
| 21 | UNIPI | Alessia Marangon |
| 22 | UPM | Eduardo Gallego |
| 22 | UPM | Emilio Migoya |
| 23 | UU | Dmitriy Makarov |
| 23 | UU | Vladimir Molkov |
| 24 | Volvo | Paul Adams |

List of Actions

Action 1	(BRE & selected participants) to consult appropriate participants to obtain information on regulations, standards and practice with respect to ventilation and tunnel emergency response in their country	7

Action 2	(BRE) to compile the gathered information on regulations etc	7

Action 3	(BMW / Volvo) to take the initiative in selecting the accident	8

Action 4	(all) to consider whether to pursue the FZK experiments as a potential SBEP (WP 3)	8

# Agenda

The meeting was held on April 22nd, 2005, starting at 10:00  and finishing at 15:00.

The agenda at adopted for the meeting (and published on the HySafe website) was as follows:

# Meeting Summary and Actions

# 1. Welcome

S Miles welcomed the participants to BRE, who then introduced themselves briefly.

# 2. Introduction to HyTunnel and Interaction with other Work Packages

The background to the Internal Project HyTunnel, and the proposed structure of the project and its interaction with the other work packages of HySafe was presented by S. Miles – see item 6 below for the contents of the presentation. Following the NGB meeting in Paris in March, HyTunnel had been added to the Joint Program of Activities (JPA) for months 13 to 30 – see item 5 below for HyTunnel project description in the current JPA.

It was noted that HSE/HSL (UK) had been omitted from the HyTunnel description in the JPA, and it was confirmed that this organisation would be participating in HyTunnel. Furthermore, the University of Ulster (UU) would contribute where appropriate to the project.

The general background to tunnel construction, ventilation, fire and smoke hazards and suppression methods is contained in the presentation (item 6) and is not repeated here. S Kumar provide some examples of precious tunnel fire and smoke hazard analysis work undertaken at BRE. HyTunnel would concentrate on road tunnels.

While it was noted that it was intended that HyTunnel extend into the JPA period for months 31 to 48 (Phase 2), the focus of the kick-off meeting was on Phase 1 (months 13 to 30). HyTunnel had been identified as Work Package 19 in the JPA for months 13 to 30.

S Miles identified five sub-tasks for Phase I:

- Sub-task 19.1	To review regulations, standards and practice for road tunnel ventilations and emergency response.

- Sub-task 19.2	To review and identify accident scenarios.

- Sub-task 19.3	To review previous physical experiments and numerical modelling work of relevance to HyTunnel.

- Sub-task 19.4	To develop a 'road map' for Phase 2 and beyond.

- Sub-task 19.5	To undertake numerical simulations.

The formal reporting structure for HyTunnel would be kept relatively simple, with two deliverables in Phase 1:

- Deliverable 1	Identified as number D49 in the JPA for months 13 to 30, this would be an activity report on sub-tasks 19.1 and 19.2. The suggested date for this was month 22 (January 2006).

- Deliverable 2	Identified as number D62 in the JPA for months 13 to 30, this would be an activity report on sub-tasks 19.3 to 19.5. The suggested date for this was month 29 (August 2006).

It had been agreed at the previous NGB meeting in Paris that participants' efforts in the internal projects would be attributed via their activity in the main work packages. This meant that the delivery of the sub-tasks for HyTunnel would formally be considered as part of the delivery of the main work packages. The main interaction of HyTunnel with the main HySafe work packages that was anticipated was summarised as follows:

- WP3 (CFD benchmarking)	Possible selection of a SBEP to support HyTunnel (sub-task 19.5)

- WP4 (PIRT)	Scenario selection for next round of PIRT process (sub-task 19.2)

- WP8 (H2 release …)	Sub-task 19.3

- WP9 (H2 ignition …)	Sub-task 19.3

- WP10 (Explosions)	Sub-task 19.3

- WP11 (mitigation - sub-task 11.5 – modelling tunnel ventilation)		Sub-task 19.5

- WP12 (Risk assessment)	Phase 2 ?

- WP16 (Standards)	Sub-task 19.1 ?

It was noted that some of the above anticipated activity would fall into Phase 2, i.e. not within the JPA for months 13 to 30.

# 3. Discussion on Tasks for Phase 1

# Details on the content, effort requirements and potential leaders for sub-tasks 19.1, 19.2, 19.3 and 19.5 (not 19.4), to be conducted in Phase 1, was held. The main points are reported below, and actions that need to be completed before month 22 are identified.

- Sub-task 19.1	It was agreed that BRE would lead this sub-task. While BRE would address the UK, North America and general international scene, other participants would requested for information for their own countries or areas. BRE would compile the information gathered.

An initial delivery date of the end of June was set for completing the information gathering exercise prior to the compilation report being written (by BRE). It is now proposed that the information be gathered by 30 September, so that the information can be compiled in good time for the Activity Report (D49) due in month 22.

(BRE & selected participants) to consult appropriate participants to obtain information on regulations, standards and practice with respect to ventilation and tunnel emergency response in their country

(BRE) to compile the gathered information on regulations etc

- Sub-task 19.2	It was agreed that BMW and Volvo would lead this sub-task, and take primary responsibility in defining the specific accident scenarios of importance. Other participants were encouraged to contribute also.

It was agreed that accident scenarios involving buses may be important, as well as the issue of liquid versus compressed gas storage.

WUT reported that it had useful information on crash statistics inside tunnels.

BMW / Volvo would present the selected accident scenarios at the next HyTunnel meeting.

(BMW / Volvo) to take the initiative in selecting the accident

- Sub-task 19.3	It was agreed that BRE would take overall lead in this sub-task, compiling the information gathered. Specific parts of the work would be led by others as follows, i.e. explosions by UU and fire by HSE/HSL.

It would be important to identify the ‘gaps in knowledge’. Close interaction with Work Package 8 was envisaged, in particular in respect to Task 8.1.

The findings from this sub-task would be included in the second HyTunnel deliverable (D62) in month 29.

- Sub-task 19.5	The degree of activity in this sub-task within Phase 1 of HyTunnel is not yet clear. Numerical simulations could be undertaken in support of the design of experiments for Phase 2 or an SBEP from Work Package 3 could be allocated to HyTunnel.

S Hawksworth presented some planned tunnel ventilation experiments involving hydrogen combustion in a force ventilated tunnel space. However, in reflection is was decided that the experiments would not be suited to a numerical modelling activity (SBEP).

A Kotchourko made a presentation on a programme of six experiments planned by FZK for Autumn 2005. This would involve an investigation of critical conditions on FA and DDT in a semi-confined enclosure. The enclosure resembles to some extent a tunnel section. Further details are given in the presentation included in these minutes under item 7 below.

There was some interest shown in adopting the FZK experiments as a potential SBEP for Work Package 3.

(all) to consider whether to pursue the FZK experiments as a potential SBEP (WP 3)

# 4. Close

# The meeting closed at 15.00.

# 5.	HyTunnel Internal Project Description in the JPA for Months 13-30

# 6.	Presentation by S. Miles on HyTunnel Background and Envisaged Structure and Interaction with other Work Packages

# 7.	Presentation by A. Kotchourko on FA and DDT Experiments

# Text boxes

not held

not held